## Dashboard
EXCLUSIVE METALS — PRODUCTION DASHBOARD
Live rollup — counts of assemblies currently at each stage. Includes Folded Metal sub-stages. Updates automatically as Detail sheet is edited.
[6 empty] | — VENDOR PROCESSING — |  |  |  | — IN-SHOP PIPELINE —
| Customer Job | EM Job / Description | Due Date | Days Out | Total Qty | Sent | At Vendor | Ready PU | Parts Proc. | Cut | Fit | Welded | Inspected | Shipped | On Hold | Status | % Done
| S&S 431 | EM 25048 Handrail |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | Ready to Ship | 88.89%
| S&S 434 | EM 25049 Handrail |  |  | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 11.11%
| S&S 465 | EM 25050 Stairs & Handrail | 09/15/2026 | 69 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 3 | 0 | Not Started | 90.56%
| S&S 469 | EM 25051 Stairs & Handrail | 09/30/2026 | 84 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 11.11%
Formulas:
Days Out = IF([Due Date]="","",IFERROR([Due Date]-TODAY(),DATEVALUE([Due Date])-TODAY()))

## Detail
DETAIL — per-assembly entry (shop workstation)
Update Current Stage on each row as work progresses. Dashboard rolls up automatically. One row per shippable assembly.
Stages (in order): | Parts Processing → Sent to Vendor → At Vendor → Ready for Pickup → Cut → Fit → Welded → Inspected → Shipped. In-house parts skip the three vendor stages.
Processing Path: | In-House = all fab done at EM. Folded Metal = larger plate/pipe/HSS sent out for cutting/forming. S&S Steel = larger channels sent out for processing. Vendor parts return for fit/weld/inspection at EM.
Hold: | Set On Hold = Yes and fill in Hold Reason. The assembly keeps its Current Stage; Dashboard shows the held count and the job's Status flips to Hold.
Adding rows: | Type into the next blank row (rows 10-209 are pre-formatted). Dashboard rollup auto-includes new rows in that range.
# | Customer Job | Mark / Assy | Description | Qty | Processing Path | Current Stage | On Hold? | Hold Reason | Crate # | Notes
▼ S&S 431 — 4 assemblies (click [-] to collapse)
1 | S&S 431 | 50600HR | Handrail Assembly | 1 | Folded Metal | Inspected | No |  |  | Built — awaiting shipment
2 | S&S 431 | 50601HR | Handrail Assembly | 1 | Folded Metal | Inspected | No |  |  | Built — awaiting shipment
3 | S&S 431 | 50807C | Channel Assembly | 1 | S&S Steel | Inspected | No |  |  | Built per Carsen — no material/routing record on file; confirm
4 | S&S 431 | 50808C | Channel Assembly | 1 | S&S Steel | Inspected | No |  |  | Built per Carsen — no material/routing record on file; confirm
▼ S&S 434 — 4 assemblies (click [-] to collapse)
5 | S&S 434 | 30600HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No |  |  | Not yet built; material ready to send to Folded Metal
6 | S&S 434 | 30601HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No |  |  | Not yet built; material ready to send to Folded Metal
7 | S&S 434 | 30602HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No |  |  | Not yet built; material ready to send to Folded Metal
8 | S&S 434 | 30603HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No |  |  | Not yet built; material ready to send to Folded Metal
▼ S&S 465 — 20 assemblies (click [-] to collapse)
9 | S&S 465 | 500GR | Guardrail Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
10 | S&S 465 | 5000HR | Handrail Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
11 | S&S 465 | 5000S | Stair Assembly | 1 | S&S Steel | Shipped | No |  |  | Shipped on S01
12 | S&S 465 | 5000S-1 | Stair Assembly | 1 | S&S Steel | Shipped | No |  |  | Shipped on S01
13 | S&S 465 | 5000VB | Vertical Brace Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
14 | S&S 465 | 5001GR | Guardrail Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
15 | S&S 465 | 5001HR | Handrail Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
16 | S&S 465 | 5002HR | Handrail Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
17 | S&S 465 | 5002P | Plate Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
18 | S&S 465 | 5003B | Beam Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
19 | S&S 465 | 5003HR | Handrail Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
20 | S&S 465 | 5003P | Plate Assembly | 1 | Folded Metal | Shipped | No |  |  | Shipped on S02
21 | S&S 465 | 5004B | Beam Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
22 | S&S 465 | 5004HR | Handrail Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
23 | S&S 465 | 5004P | Plate Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
24 | S&S 465 | 5005HR | Handrail Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
25 | S&S 465 | 5006HR | Handrail Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
26 | S&S 465 | 5006P | Plate Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
27 | S&S 465 | 5007HR | Handrail Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
28 | S&S 465 | 5012P | Plate Assembly | 1 | Folded Metal | Inspected | No |  |  | Built; shipped-vs-staged split pending (BOLs S01/S02 drafted). Path inferred from standard routing (QM-003) — confirm
▼ S&S 469 — 16 assemblies (click [-] to collapse)
29 | S&S 469 | 8000GR | Guardrail Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
30 | S&S 469 | 8000HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
31 | S&S 469 | 8000L | Ladder Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
32 | S&S 469 | 8000S | Stair Assembly | 1 | S&S Steel | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
33 | S&S 469 | 8001GR | Guardrail Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
34 | S&S 469 | 8001HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
35 | S&S 469 | 8001S | Stair Assembly | 1 | S&S Steel | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
36 | S&S 469 | 8002GR | Guardrail Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
37 | S&S 469 | 8002HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
38 | S&S 469 | 8002S | Stair Assembly | 1 | S&S Steel | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
39 | S&S 469 | 8003GR | Guardrail Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
40 | S&S 469 | 8003HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
41 | S&S 469 | 8004GR | Guardrail Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
42 | S&S 469 | 8004HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
43 | S&S 469 | 8005GR | Guardrail Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
44 | S&S 469 | 8005HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No | Awaiting drawing & file revisions before release to Folded Metal |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
45 | S&S 469 | 8006HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No |  |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
46 | S&S 469 | 8007HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No |  |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.
47 | S&S 469 | 8008HR | Handrail Assembly | 1 | Folded Metal | Parts Processing | No |  |  | In production — revisions received. Path inferred from standard routing (QM-003) — confirm.

## Parts
PARTS — per-stock-type heat traceability (per assembly)
One row per stock type per assembly. Heat # is captured by DCC at receipt (in-house material) or from QC-002-F2 work order (outside processed). Detail tab Heat #(s) column auto-rolls up from this sheet.
Edge case: if same stock type came from MULTIPLE heats for one assembly, split the row — same Assembly Mark + Stock Type, different Piece Marks subsets, different Heat #.
# | Job | Assembly Mark | Stock Type | Piece Marks Included | Qty | Heat # | Notes
S&S 431 — EM 25048 Handrail
1 | S&S 431 | 50600HR | PI 1-1/2 SCH40 | 50600HR, pi7 (x3), pi8 (x5), pi9 (x4), pi10 (x2) | 15 | 202603447 | Main rail + posts
2 | S&S 431 | 50600HR | PI 1-1/2 SCH80 | pi1 (x2), pi2 (x3), pi5, pi6 | 7 | 15298321A2 | Heavy-wall pieces
3 | S&S 431 | 50600HR | L 6x3-1/2x3/8 | a1 (x7) | 7 | HA077453 | Angle clips (recv desc: L 6x4x3/8)
4 | S&S 431 | 50600HR | PL 1/4" x 4" | pL6, pL7, pL11 | 3 | 15291861A1
5 | S&S 431 | 50601HR | PI 1-1/2 SCH40 | 50601HR, pi4 (x6) | 7 | 202603447 | Main rail
6 | S&S 431 | 50601HR | PI 1-1/2 SCH80 | pi1 (x2), pi2 (x2) | 4 | 15298321A2 | Heavy-wall pieces
7 | S&S 431 | 50601HR | L 6x3-1/2x3/8 | a1 (x4) | 4 | HA077453 | Angle clips
8 | S&S 431 | 50601HR | PL 1/4" x 4" | pL12 | 1 | 15291861A1
S&S 434 — EM 25049 Handrail (4 rails)
9 | S&S 434 | 30600HR | FB 1/4" x 4" | pL312 | 1 | 15291861A1
10 | S&S 434 | 30600HR | PL 1/2" x 5" | pL928 (x3) | 3 |  | Heat not in receiving log — pre-traceability
11 | S&S 434 | 30600HR | ROD 1-3/8" | m142 (x3) | 3 | P1375318
12 | S&S 434 | 30601HR | FB 1/4" x 4" | pL323 | 1 | 15291861A1
13 | S&S 434 | 30601HR | PL 1/4" x 2-1/2" | pL356 | 1 | 202601934
14 | S&S 434 | 30601HR | PL 1/2" x 5" | pL928 (x3) | 3 |  | Heat not in receiving log — pre-traceability
15 | S&S 434 | 30601HR | ROD 1-3/8" | m142 (x3) | 3 | P1375318
16 | S&S 434 | 30602HR | FB 1/4" x 4" | pL325, pL926 | 2 | 15291861A1
17 | S&S 434 | 30602HR | PL 1/4" x 2-1/2" | pL356 | 1 | 202601934
18 | S&S 434 | 30602HR | PL 1/2" x 5" | pL928 (x4), pL929 | 5 |  | Heat not in receiving log — pre-traceability
19 | S&S 434 | 30602HR | ROD 1-3/8" | m142 (x5) | 5 | P1375318
20 | S&S 434 | 30603HR | FB 1/4" x 4" | pL926, pL927 | 2 | 15291861A1
21 | S&S 434 | 30603HR | PL 1/4" x 2-1/2" | pL356 | 1 | 202601934
22 | S&S 434 | 30603HR | PL 1/2" x 5" | pL928 (x4), pL929 | 5 |  | Heat not in receiving log — pre-traceability
23 | S&S 434 | 30603HR | ROD 1-3/8" | m142 (x5) | 5 | P1375318
24 | S&S 434 |  | PI 1" STD | (job-level — pipe pkg not filed) | 1 | HP004459 | Pipe manifest absent; heat job-level, assembly attribution pending
25 | S&S 434 |  | PI 1-1/2" SCH80 | (job-level — pipe pkg not filed) | 3 | 15298321A2 | Assembly attribution pending
26 | S&S 434 |  | PI 1-1/2" STD | (job-level — pipe pkg not filed) | 8 | 202603447 | Assembly attribution pending
S&S 465 — EM 25050 Stairs & Handrail
27 | S&S 465 |  | C 6x2.157x.437 |  | 1 | 202603986 | Job-level heat capture from receiving log; per-assembly attribution pending (built before full traceability). Assembly Mark intentionally blank.
28 | S&S 465 |  | C 8x2.527x.487 |  | 2 | 15314241A1
29 | S&S 465 |  | C 12x2.96x.300 |  | 2 | 25679709 (x2) / 14894212A1 (x2) | Multiple heats — cannot split without consumption record
30 | S&S 465 |  | FB 1/4" x 2" |  | 1 | 15266521A1
31 | S&S 465 |  | FB 1/4" x 2-1/2" |  | 1 | 202601934
32 | S&S 465 |  | FB 1/4" x 4" |  | 24 | 15267031A1
33 | S&S 465 |  | FB 3/8" x 3-3/4" |  | 1 | 63435048 | Replaced returned 3/8x1/2 (heat 202605385)
34 | S&S 465 |  | FB 3/8" x 3" |  | 1 | 15241481A1
35 | S&S 465 |  | FB 3/8" x 6" |  | 1 | 65018273
36 | S&S 465 |  | FB 3/8" x 8" |  | 1 | 15313061A1
37 | S&S 465 |  | FB 1/2" x 5" |  | 4 | HK299860
38 | S&S 465 |  | FB 1/2" x 12" |  | 1 | 150482101A1
39 | S&S 465 |  | FB 5/8" x 8" |  | 1 | 15254351A1
40 | S&S 465 |  | FB 3/4" x 12" |  | 1 | 15227311A1 | Substituted for 5/8x12 (no bid)
41 | S&S 465 |  | L 1-1/2x1-1/2x3/16 |  | 1 | 31872251A
42 | S&S 465 |  | L 2-1/2x2-1/2x1/4 |  | 1 | 31854911A
43 | S&S 465 |  | L 4x4x3/8 |  | 1 | 15305521B2
44 | S&S 465 |  | PI 1" SCH40 |  | 1 | 31857311A
45 | S&S 465 |  | PI 1-1/2" SCH80 |  | 13 | 31845511A
46 | S&S 465 |  | PI 1-1/2" SCH40 |  | 37 | 25689283 / 15253851A1 (x2) / 202600271 (x34) | Multiple heats — cannot split without consumption record
47 | S&S 465 |  | ROD 1-3/8" |  | 3 | P1375318
48 | S&S 465 |  | ROD 3/4" |  | 1 | 30854711A
49 | S&S 465 |  | PL 5/8" x 60.5 x 144.5 |  | 1 | 649848B9 | PO-465-001
S&S 469 — EM 25051 Stairs & Handrail
50 | S&S 469 |  | C 6x2.157x.437 |  | 1 | 202603986 | Job-level heat capture from receiving log; per-assembly attribution pending (built before full traceability). Assembly Mark intentionally blank. ¦ Status: Ordered
51 | S&S 469 |  | C 12x2.96x.300 |  | 2 | 14894212A1 | Ordered
52 | S&S 469 |  | FB 3/16" x 2" |  | 1 | 25774852 | Received
53 | S&S 469 |  | FB 1/4" x 2" |  | 1 | 15312011A1 | Ordered
54 | S&S 469 |  | FB 1/4" x 3" |  | 1 | 202600661 | Received
55 | S&S 469 |  | FB 1/4" x 4" |  | 5 | 15267031A1 | Ordered
56 | S&S 469 |  | FB 3/8" x 3" |  | 3 | 15241481A1 | Ordered
57 | S&S 469 |  | FB 1/2" x 8" |  | 1 | 15305511A1 | Received
58 | S&S 469 |  | L 1-1/2x1-1/2x3/16 |  | 1 | 15336511A2 | Ordered
59 | S&S 469 |  | PI 1-1/2" SCH40 |  | 19 | 15333611A1 | Ordered
60 | S&S 469 |  | PI 1-1/2" SCH80 |  | 7 | 31871811A | Ordered
61 | S&S 469 |  | ROD 1-3/8" |  | 2 | P1375318 | Ordered
62 | S&S 469 |  | ROD 3/4" |  | 1 | 25757370 | Corrected from 2577370 (Coast paperwork typo). MTR 25757370.pdf. Shared 465/469 stock per known purchasing consolidation — cross-job heat sharing expected.

## Lookups
JOB COLOR PALETTE |  |  | PRODUCTION STAGES (in order)
Color Name | Hex Code | Sample | # | Stage Name | Color | Meaning
Red | D32F2F |  | 1 | Parts Processing |  | Work order opened, drawing pulled, material allocated. Decisions made on path (In-House vs Folded Metal). Nothing physical yet.
Blue | 1E63B5 |  | 2 | Sent to Vendor |  | Material has been delivered or shipped to the vendor (Folded Metal or S&S Steel) for cutting/forming. Awaiting vendor confirmation of receipt.
Green | 2E8B3D |  | 3 | At Vendor |  | The vendor has the parts and is actively processing them. DCC has confirmed work-in-progress with vendor.
Black | 1F1F1F |  | 4 | Ready for Pickup |  | The vendor has finished. Parts are at the vendor waiting for EM to pick them up. This is an action-required state — schedule a pickup run.
Yellow | F5C518 |  | 5 | Cut |  | Material is in its final cut/formed state IN-HOUSE, ready for fit. Either in-house cut, OR received back from a vendor (Folded Metal/S&S Steel).
|  |  | 6 | Fit |  | Parts are fit/assembled prior to weld (mock-up complete).
|  |  | 7 | Welded |  | Welding complete. Awaiting QC inspection &#x2014; weld integrity, dim verify, finish check.
|  |  | 8 | Inspected |  | QC inspection complete (welds, dims, finish all verified per QC checklist). Ready to be staged for shipment.
|  |  | 9 | Shipped |  | Out the door. Reference the shipper number (e.g., S01) in Notes.
PROCESSING PATHS
|  |  | In-House |  |  | All cutting, forming, fitting, and welding done at EM.
|  |  | Folded Metal |  |  | Larger plate / pipe / HSS material sent to Folded Metal for cutting/forming. EM does fit and weld in-house after parts are received back.
|  |  | S&S Steel |  |  | Larger channels sent to S&S Steel for processing. EM does fit and weld in-house after parts are received back.

## Instructions
How to use the Production Tracker (QC-006-F1)
Purpose | A single live view of where every active job is in the production pipeline. Designed to broadcast on the shop TV (Dashboard sheet) and updated from the shop workstation (Detail sheet).
Sheets | Detail sheet = data entry. One row per shippable assembly. Floor updates Current Stage as work progresses. Dashboard sheet = read-only rollup, one row per job. Parts sheet = per-stock-type heat traceability (per assembly); DCC owns this — used when heat # capture is required per customer. Lookups and Instructions are reference.
Workflow | 1) New job kicks off → add a Dashboard row (Job #, Color, Description, Due Date). 2) DCC seeds the Detail sheet with one row per shippable assembly; sets Processing Path = In-House, Folded Metal, or S&S Steel; initial Current Stage = Parts Processing. 3) Shop foreman updates Current Stage at the workstation as each assembly progresses. 4) When an assembly ships, Current Stage → Shipped, add note referencing shipper number (e.g., "On S01").
Stages (all 9, in order) | Parts Processing → Sent to Vendor → At Vendor → Ready for Pickup → Cut → Fit → Welded → Inspected → Shipped. Stages 2-4 apply only to assemblies routed through a vendor (Folded Metal or S&S Steel). In-house parts skip them and go from Parts Processing directly to Cut.
Vendor processing lifecycle | Sent to Vendor: material physically left EM, awaiting vendor confirmation of receipt. At Vendor: vendor has confirmed they're working on the parts. Ready for Pickup: vendor finished — schedule a pickup. Once picked up and back at EM, advance to Cut (the parts are now in cut form in-house, ready for fit).
Partial FM batches | If Folded Metal returns only some components of an assembly (e.g., 3 of 5 plates back, 2 still at FM), keep Current Stage at the worst remaining state — typically 'At Vendor' or 'Ready for Pickup'. Use the Notes column to track the breakdown: '3 of 5 received [date]. Awaiting 2 from FM.' Only advance Current Stage to Cut once ALL components are physically back at EM. Rule of thumb: assembly's stage = the earliest stage any of its components is at.
Hold | Set On Hold = Yes and fill in Hold Reason. The assembly keeps its Current Stage; Dashboard shows held count and job's Status flips to Hold. Hold reasons should be specific: "Awaiting drawing rev confirmation" not "Stuck."
Parts tab | One row per stock type per assembly. Captures which heat # was used for which piece marks. Owned by Document Control. Not currently active for shop floor — DCC will populate as heat capture becomes required (e.g., customer spec, code work). Job header rows are colored to match the Dashboard palette and data rows collapse under each job header (click the [-] outline button at the top-left). Edge case: if a single stock type came from multiple heats for the same assembly, split the row — same Assembly Mark + Stock Type, different Piece Marks subsets, different Heat #.
Crate # | When the crate builder loads an assembly into a shipping crate, they write the crate number on the Detail row. Format: 'C-01', 'C-02' for crates within a single shipment, or shipper-prefixed (e.g., 'S03-C01'). This links each assembly to its physical shipping container so the shipper docx (QC-006-F2) can be filled out from this data.
Color coding | Each job gets a single color from the palette in Lookups. The same color is used to physically mark material on the floor (paint pen, tag, etc.) so shop personnel can match material to a job at a glance. Dashboard shows the color band on the left of each job's row.
Dashboard logic | Each stage column shows the COUNT OF ASSEMBLIES CURRENTLY AT THAT EXACT STAGE for the job. So you can see distribution at a glance: e.g., '0 Parts Proc, 1 Sent, 2 At Vendor, 1 Ready PU, 1 Cut, 0 Fit, 3 Welded, 2 Inspected, 2 Shipped' tells you exactly where each piece is.
Status column | Derived from rollup. Hold beats everything. Then Shipped (all shipped), Ready to Ship (all inspected), At Vendor (anything at a vendor stage), In Fab (any in-shop work after Parts Processing), otherwise Not Started.
Days Out | Calculated from Due Date. Red when <7 days, yellow at 7-14 days.
Adding new jobs | Insert a new row in the Dashboard between row 5 and the last job. Fill in Job #, Color, Description, Due Date — copy the stage/count formulas from the row above. Then seed Detail with one row per assembly.
Adding new assemblies mid-job | Type into the next blank row on Detail (rows 10-209 are pre-formatted with dropdowns). Dashboard rollup will automatically include them.
Range limit | Dashboard formulas reference Detail rows 10-209 (200 rows). If a single job ever exceeds that, formulas need updating. Tell Document Control if this becomes a constraint.
Retention | Per QC-006 §15, retained 7 years from job close. At job close, archive workbook to 02_Closed Jobs/[Year]/[Job#]/.